## Sheet1
Retrospective Action Items & Lessons Learned
Reference(s): https://agilestrides.com/blog/40-ideas-to-spice-up-your-retrospective/ ;
Status | Sprint ID | Issue | Action Item | Discussion | Owner(s) | Result | Notes
Implemented | 47 | Too much review and QA prior end of sprint | End code deployments on Thursday | Cut a version tag and freeze code on Thursday afternoon | Daniel / Bob | Tried during Sprints 48 and 48; worked well.